## Slide 1: Software engineering module – II Management
Semester VI B.Tech. CSE Viswajyothi College of Engineering

## Slide 2: Why Project Fail?
Changing customer requirement
Ambiguous/Incomplete requirement
Unrealistic deadline
An honest underestimate of effort
Predictable and/or unpredictable risks
Technical difficulties
Miscommunication among project staff

## Slide 3: Management
The art of getting work done through other people.
"The creation and maintenance of an internal environment in an enterprise where individuals, working together in groups, can perform efficiently and effectively toward the attainment of group goals" (Koontz et al, 1980)

## Slide 4: Management Functions
Planning
  Determine the flow of information, people, and products.
Organizing
  Establishment of clear line of authority and responsibility.
Staffing
  Hiring, compensating, developing and promoting employees.
Directing
  Leading Subordinates.
Controlling
  Measuring and Correcting activities

## Slide 5: Project Planning
Define and document the assumptions, goals, and constraints of the project.
Plan for how best to meet the requirements within the constraints.
  Process model, resources, cost, schedule.
Software Productivity
  People & Process
  Basis for estimating resource requirements.
  Basis for evaluating the performance of individuals, processes, and tools etc.
  If it can be measured quantitatively;
    Can make improvements.
  Factors affecting productivity
    Professionals' capabilities, Product complexity, Schedule constraints, Previous experience

## Slide 6: Contnd..
Productivity Metrics
  Source Lines Produced per unit time.
    Not a measure of quality.
  Amount of value or Functionality produced per unit time.
    Difficult to quantify.
  Function Points
Not used to measure the ability or the productivity of a s/w engineer.

## Slide 7: Contnd..
Cost Estimation
  Primary cost is for people.
  Uses
    To decide the number of engineers needed for the project and develop a schedule during the planning stage.
    Monitor the projects progress.
  Project size is used as a basis for determining the effort and thus the costs and time associated with the later stages of SDLC.

## Slide 8: Generic formula for effort
PM = c.KLOCk
  PM: person month
  KLOC: K lines of code
  c, k depend on the model
  k>1 (non-linear growth)
Initial estimate then calibrated using a number of "cost drivers"

## Slide 9: Typical cost driver categories
Product
  e.g., reliability requirements or inherent complexity
Computer
  e.g., are there execution time or storage constraints?
Personnel
  e.g., are the personnel experienced in the application area or the programming language being used?
Project
  e.g., are sophisticated software tools being used?

## Slide 10: Cost estimation procedure
Estimate software size, and use it in the model’s formula to get initial effort estimate
Revise estimate by using the cost driver or other scaling factors given by the model
Apply the model’s tools to the estimate derived in step 2 to determine the total effort, activity distribution, etc.

## Slide 11: Constructive Cost Model (COCOMO)
A set of three different models of increasing complexity and level of detail.
Size estimate based on delivered source instructions, KDSI
Categorizes the software as:
  Organic
  Semidetached
  Embedded
    Each has an associated formula for nominal development effort based on estimated code size.

## Slide 12: Contnd..
Mode
Feature
Organic
Semidetached
Embedded
Organizational understanding of
product objectives
Thorough
Considerable
General
Experience in working with related
software systems
Extensive
Considerable
Moderate
Need for software conformance with
pre
-
es
tablished requirements
Basic
Considerable
Full
Need for software conformance with
external interface specifications
Basic
Considerable
Full
Concurrent development of
associated new hardware and
operational procedures
Some
Moderate
Extensive
Need for inn
ovative data processing
architectures, algorithms
Minimal
Some
Considerable
Premium on early completion
Product size range
Low
<50 KDSI
Medium
<300 KDSI
High
All sizes

## Slide 13: Contnd..
Determine the effort multiplier based on the cost-driver attributes (15 Nos).
  Multipliers are multiplied together.
  Product is again multiplied by the nominal effort.

## Slide 14
Ratings
Cost Drivers
Very low
Low
Nominal
High
Very
High
Extra
High
Product attributes
Required software
reliability
.75
.88
1.00
1.15
1.40
Data base size
.94
1.00
1.08
1.16
Product complexity
.70
.85
1.00
1.15
1.30
1.65
Comput
er attributes
Execution time constraints
1.00
1.11
1.30
1.66
Main storage constraints
1.00
1.06
1.21
1.56
Virtual machine volatility*
.87
1.00
1.15
1.30
Computer turnaround time
.87
1.00
1.07
1.15
Personnel attributes
Anal
yst capability
1.46
1.19
1.00
.86
.71
Applications experience
1.29
1.13
1.00
.91
.82
Programmer capability
1.42
1.17
1.00
.86
.70
Virtual machine
experience*
1.21
1.10
1.00
.90
Programming language
experience
1.14
1.07
1.00
.95
Project
attributes
Use of modern
programming practices
1.24
1.10
1.00
.91
.82
Use of software tools
1.24
1.10
1.00
.91
.83
Required development
schedule
1.23
1.08
1.00
1.04
1.10
COCOMO
scaling
factors

## Slide 15: Contnd..
Maintain a project database
  Progress information
  Uses
    To validate a particular cost estimation model against past projects.
    To calibrate cost-driver or scaling factors for a model.
      Based on organization’s environment.
    As a basis for arriving at an initial size estimate.
    To calibrate estimates of effort that are derived from a model.

## Slide 16: COCOMO II
Deficiencies of COCOMO
  Assumption about process model.
    Traditional models
  Reliance on lines of code as an estimator.
Difference of COCOMO II
  More proper collection of three models
    Application Composition Model
    Early Design Model
    Post-Architecture Model
  Uses different models for software size.
    With different ranges of accuracy
    Object point to LOC.

## Slide 17: Contnd..
Application Composition Model
  Suitable for software built around graphical user interface (GUI) and modern GUI-builder tools.
  Uses object points as a size metric
    Extension of function points
    Count of the screens, reports, and modules, weighted by a three-level factor (simple, medium, difficult)
Early Design Model
  Used once requirements are known and alternative software architectures have been explored.
  Cost prediction based on function points and coarse-grained cost drivers.
    e.g., personnel capability and experience

## Slide 18: Contnd..
Post-Architecture Model
  Involves actual software construction and software maintenance.
  Cost prediction based on
    Size (either as source instructions or function points, with modifiers to account for reuse)
    17 multiplicative cost drivers
    5 factors that determine the non linear growth of person-month costs in terms of size

## Slide 19: Project Control
To monitor the progress against the plans.
To detect deviations from the plan.
To take corrective actions.
  Plan realistically to minimize the need for corrective action.
Work Breakdown Structure
  WBS describes a break down of project goal into intermediate goals.
    Each in turn broken down in a hierarchical structure
    Builds a tree whose root is the major activity of the project.
    Each leaf represents a piece of work whose estimates can be confidently made.
  Plan for each goal individually.

## Slide 20: Contnd..
Goal of WBS is to identify all the activities that a project must undertake.
A basis for estimating the resources necessary for the project as a whole
  Estimate resources required for each leaf.
A basis for work assignment.
Used as an input to the scheduling process.
  Decomposition – > which task need to be done.
  Scheduling – > order in which to do task

## Slide 21: Contnd..
Gantt Charts
  A project control technique
  Defined by Henry L. Gantt
  Used for several purposes, including scheduling, budgeting, and resource planning
  A bar chart,
    Each bar representing an activity.
    Drawn against the timeline.
    The length of each bar is proportional to the length of time planned for the activity.
  It does not identify activities.

## Slide 23: Contnd..
In standard Gantt chart bar length shows actual duration.
In enhanced version;
  White part shows actual duration.
  Gray part shows the slack time.
  Bar with full white part for a tsk with no slack time.
Uses
  Allocate resources and plan staffing.
Does not highlights inter-task dependencies.

## Slide 24: Exercise 1
A project has been defined to contain the following list of
activities along with their required times for completion.
Activity Time (weeks) Immediate Predecessors
A-collect requirements 2 -
B-analyze processes 3 A
C-analyze data 3 B
D-design processes 7 B
E-design data 6 B
F-design screens 1 C, D
G-design reports 5 D, E
H-programming 4 F, G
I-test and document 8 G
J-install 2 H, I

## Slide 25
A
B
C
D
E
F
G
H
I
J
Start
0 5 10 15 20 25 30

## Slide 26: Contnd..
PERT (Program Evaluation and Review Technique) Chart
  A network of boxes (or Circles) and arrows.
  Activities are represented in boxes or arrows.
    Starting and ending dates can be shown in the boxes.
    Can designate as a milestone.
      An activity whose completion signals an important accomplishment in the life of the project.
  Arrow shows the dependencies of activities on one another.
    Activity at the head of an arrow can not start until the activity at the tail of the arrow is finished.

## Slide 27: Contnd..
Steps
  List all activities
  Estimate the duration of each activity.
  Determine the dependence of the activities on each other.
  Prepare PERT
  Compute Earliest start or finish dates and latest start or finish dates.

## Slide 28: Analysis of PERT charts
Critical path for the project (shown in bold)
  Path in which any delay in any activity causes a delay in the entire project
    Activities on the critical path must be monitored more closely than other activities.
Salient Features
  Force and helps the manager to plan
  Show interrelationships among tasks
    Clearly identifies the critical path
    Allows to consider alternative approaches to cope with a potential problem
  Exposes parallelism in the activities
    Helps in allocating resources
  Allow scheduling and simulation of alternative schedules
  Enable the manager to monitor and control project

## Slide 29: Contnd..
Gantt Vs PERT
  Gantt – Planning and utilization of resources.
  PERT – Monitoring of process.